## Slide 1
N C R M P Phase-II
8th Project Steering Committee Meeting
19thJanuary 2018

## Slide 2: NCRMP Phase II
6 States - Goa, Gujarat, Karnataka, Kerala, Maharashtra & West Bengal.
Outlay: Rs 2361.35 Cr.(GoI: Rs.1881.20 Cr, State: Rs. 480.15 Cr.)
Commenced on 24th July 2015 with closure stipulated by 31st March, 2020.

## Slide 3: AGENDA ITEM (I) FINANCIAL MANAGEMENT Outlay/Expenditure/Unspent Balance
1/5
Goa
Outlay: Rs 140.00 Cr ; Released: Rs 24.16 C
(GoI 112.25 State 27.75) (GoI 24.16 State: NIl )
Expenditure: Rs Cr 1.24 Unspent balance: Rs 22.92 Cr
(GoI: 1.24State:Nil) (GoI:22.92; State Nil)
II. Gujarat
Outlay: Rs 618.50 Cr; Released: Rs 210.45 Cr
    (GoI:476.00 State:142.50) (GoI:175.02 State: 35.43)
Expenditure: Rs 149.15 Cr Unspent balance: Rs 61.30Cr
    (GoI: 113.72 State:35.43) (GoI: 61.30; State: Nil)

## Slide 4: AGENDA ITEM (I) FINANCIAL MANAGEMENT Outlay/Expenditure/Unspent Balance
2/5
III Karnataka
Outlay: Rs 128.20 Cr; Released: Rs 12.45 Cr
  (GoI 99.90 State 28.30) (GoI 12.45 State: Nil )
Expenditure: Rs 0.76 Cr Unspent balance: Rs 11.69 Cr
    (GoI: 0.76 State:Nil) (GoI:11.66; State Nil)
IV. Kerala
Outlay: Rs 158.95Cr; Released: Rs 6.44Cr
    (GoI:124.95 State:34.00) (GoI:6.44 State: Nil)
Expenditure: Rs 1.01Cr Unspent balance: Rs5.43Cr
    (GoI:1.01 State:Nil) (GoI: 5.43 State: Nil)

## Slide 5: AGENDA ITEM (I) Financial Management Outlay/Expenditure/Unspent Balance
3/5
V Maharashtra
Outlay: Rs 397.95 Cr; Released: Rs 34.12Cr
  (GoI 313.20 State 84.75) (GoI 34.12 State: Nil )
Expenditure: Rs 3.10 Cr Unspent balance: Rs 31.02Cr
    (GoI: 3.10 State:Nil) (GoI:31.02; State Nil)
VI. West Bengal
Outlay: Rs 705.45Cr; Released: Rs 462.98Cr
    (GoI:542.60 State:162.85) (GoI:385.58 State: 77.40)
Expenditure: Rs 316.86 Cr Unspent balance: Rs146.12Cr
    (GoI:239.46 State:77.40) (GoI: 146.12; State: Nil)

## Slide 6
State |  | Budget Projection 2017-18 |  | Fund Release During 2017-18 | Fund released so far since inception(GOI) | Expenditure so far (GOI) |  | Unspent Balance (GOI) | Release anticipated in last quarter of 2017-18(GOI) | 
A. Goa : Outlay Rs 140.00 Crore |  |  |  |  |  |  |  |  | Total | Remarks
 |  | 23.56 |  | Nil | 24.16 |  | 1..24 | 22.92 | 0.16 | Comp C -Rs 0.16 Crore
B. Gujarat : Outlay Rs 618.50 Crore |  |  |  |  |  |  |  |  |  | 
 |  | 231.29 |  | Nil | 175.02 |  | 113.72 | 61.30 | 46.35 | Component B -Rs 44.17 Cr (on receipt of utilization unspent amount of Rs 59 Cr). Timeline? Component C – Rs. 2.18 Crore
C .Karnataka : Outlay Rs 128.20 Crore |  |  |  |  |  |  |  |  |  | 
 | 8.50 |  | Nil |  | 12.45 |  | 0.76 | 11.69 | 0.12 | Component C- Rs 0.12 Crore
AGENDA ITEM (I): FINANCIAL MANAGEMENT
Release/Expenditure/Unspent Balance
4/5
Rs in Crores

## Slide 7
State | Budget Projection 2017-18 | Fund Release During 2017-18 (GOI) | Fund Release so far since inception(GOI) |  |  | Expenditure so far(GOI) |  |  | Unspent Balance(GOI) | Release anticipated in last quarter of 2017-18(GOI) | 
D. Kerala : Outlay Rs 158.95 Crore |  |  |  |  |  |  |  |  |  | Total | Remarks
 | 9.00 | Nil | 6.44 |  | 1.01 |  | 5.43 |  |  | 2.08 | Component C - Rs 1.48 Crore Component D - Rs 0.60 Crore (on receipt of utilization unspent amount of Rs. 0.03 Cr).
E. Maharashtra : Outlay Rs 397.95Crore |  |  |  |  |  |  |  |  |  |  | 
 | 90.80 | Nil |  | 34.12 | 3.10 |  |  | 31.02 |  | 3.25 | Component C - 1.25.Crore Component D -Rs 2.00 Cr (on receipt of full utilization of unspent balance of Rs. 1.97 Cr)
F. West Bengal : Outlay Rs 705.45 Crore |  |  |  |  |  |  |  |  |  |  | 
 | 192.30 | 115.38 |  | 385.58 | 239.46 |  |  | 146.12 |  | 1.60 | Component C- Rs 1.60 Crore
 |  |  |  |  | Total to be released in Last Qtr |  |  |  |  | 44.17 06.79 02.60 | Component B Component C Component D
AGENDA ITEM (I): FINANCIAL MANAGEMENT
Release/Expenditure /Unspent Balance
5/5
Rs in Crores

## Slide 8
Position | Filled up | Vacant | Remarks
Project Manager | Kerala,Karnataka,Gujarat,Goa,Maharashtra,West-Bengal | -- | KPMG engaged as PMC in Gujarat & Maharashtra States to expedite filling up vacant positions
Sector (Engg.) Expert | Karnataka, Gujarat, Goa, Maharashtra, West-Bengal | Kerala | 
Financial Specialist | Gujarat,Goa,Maharashtra,West-Bengal | Kerala & Karnataka | 
Procurement Specialist | Kerala, Karnataka, Gujarat, West-Bengal | Maharashtra & Goa | 
AGENDA ITEM (II)- FILLING UP VACANT POSITIONS IN SPIUs
Standard Staffing Pattern And Current Position

## Slide 9: Contd..
Position | Filled up | Vacant | Remarks
Environment Specialist | Karnataka,Gujarat,Maharashtra,West-Bengal | Kerala & Goa | KPMG engaged as PMC in Gujarat & Maharashtra States to expedite filling up vacant positions
Social Management Specialist | Karnataka,Gujarat,Maharashtra, West Bengal | Kerala,Goa | 
Support Staff (MIS/IT) | Kerala,Karnataka,Gujarat, Goa Maharashtra | West Bengal | 

## Slide 10: AGENDA ITEM (III): COMPONENT A Early Warning Dissemination System(EWDS)
Goa: TCIL appointed as Knowledge Partner (May 2017) . Survey work in progress. Combination of Satellite Technology and DMR Technology Option finalised.
Gujarat: KPMG Knowledge Partner. Satellite based modified Technology finalised. RFP under finalization
Karnataka: TCIL engaged as Knowledge Partner (December 2017).Survey work being taken up by TCIL.
Kerala: TCIL Knowledge Partner. However, contract agreement not yet signed.

## Slide 11: Contd..
Maharashtra: TCIL engaged as Knowledge Partner . Kick-off meeting held on 30th Nov, 2017. Technology Option getting finalised. RFP/ Award of work by April, 2018.
West Bengal: RFP floated to engage Knowledge Partner. Bids under evaluation.
TIMELINE FOR RFP/AWARD OF WORK FORSUPPLY/COMMISSIONING OF EWDS?

## Slide 12: AGENDA ITEM (IV) COMP. B : CYCLONE RISK MITIGATION INFRASTRUCTURE Physical Progress- GOA
MPCS (16 Nos.) : One MPCS under construction , Tenders under evaluation for 7 sites. Timeline for finalisation?
-Tenders for remaining sites to be floated by February ,2018.
Roads : (30 Kms) : Dropped, keeping in view availability of good network. Savings to be utilised for other works under Component B.
Saline Embankment (2 no/13km) : Design of the Diwar Bund finalized by World Bank. EIA /SIA study completed and report under review by Bank.
Underground Cabling : (25 Km) Site for Underground Cabling identified at Anjuna Beach. DPR prepared by Discom is under review with SPIU for compliance of World Bank observations (since last 4 months). EIA/SIA underway.
Timeline for Finalisation of DPR/ Tendering ?
1/6

## Slide 13: AGENDA ITEM (IV) COMP. B : CYCLONE RISK MITIGATION INFRASTRUCTURE Physical Progress- GUJARAT
MPCS (100 Nos.): 22 completed; 4 under construction;28 tenders under evaluation ( to be awarded by end of January, 2018);46 to be tendered out by end of January, 2018.
  Status of handing over of completed cyclone shelters, formation of CSMMC, provision of Corpus fund?
Roads (43 Nos/156.74km.) : 27 Nos/99.53 km completed. 12 no/ 52.12 km under construction . Tenders to be invited for 4 roads by end of January, 2018.
Underground Cabling (430 km) :. EIA/SIA study under progress. Report submission to World Bank by 10th Feb 2018. DPR preparation to follow.
Timeline for finalisation of DPR?
2/6

## Slide 14: AGENDA ITEM (IV) COMP. B : CYCLONE RISK MITIGATION INFRASTRUCTURE Physical Progress- KARNATAKA
  MPCS (10Nos.):7 MPCS under construction .Tenders for all other sites of MPCS will be issued shortly.
  Roads (48Kms)-15 roads of 43km length awarded. Balance roads under finalisation.
  Bridges (2)- Structural Design reviewed by World Bank.DPR to be submitted by State.
  Saline Embankment (7 Kms)-Revised design for Manikatte Saline Embankment under review with SPIU for compliance of observations of World Bank. Tenders under evaluation for engaging EIA/SIA Consultant for Bridges and Saline Embankment
  Timeline for finalization of DPR/Award of Work??
3/6

## Slide 15: AGENDA ITEM (IV) COMP. B : CYCLONE RISK MITIGATION INFRASTRUCTURE Physical Progress- KERALA
MPCS (27 Nos.) :
  Architectural Drawings for 03 Sites approved by World Bank
  14 more Architectural Drawings prepared.
  DPR for Mararikulam site under review with SPIU for compliance of observations of World Bank.
  Timeline for finalisation of DPR/ Award of Work??
4/6

## Slide 16: AGENDA ITEM (IV) COMP. B : CYCLONE RISK MITIGATION INFRASTRUCTURE Physical Progress- MAHARASHTRA
MPCS (13 Nos.) :DPR for Saitwade under preparation, bid documents to be uploaded on STEP by SPIU and to be tendered out by February, 2018. Tenders for 2 other sites also to be floated by 15th March, 2018. Site selection process in progress for remaining sites.
Saline Embankment (8 no./50 Kms.) : Re-alignment survey completed & EIA/SIA study report being revised, based upon which DPR to be modified. All 8 sites to be tendered out by 15th March,2018.
Underground Cabling (130 Kms.) :Consumer survey completed for Alibagh, Ratnagiri and Satpati towns. CRZ obtained for Alibagh.DPR and bid documents of Alibagh to be shared with World Bank after incorporating technical suggestions. Tenders for Alibagh to be floated by 15th February,2018.. CRZ clearance for Ratnagiri and Satpati towns under process and to be tendered out by 7th March,2018
5/6

## Slide 17: AGENDA ITEM (IV) COMP. B : CYCLONE RISK MITIGATION INFRASTRUCTURE Physical Progress- WEST BENGAL
MPCS(150 no)- All works awarded. Work under progress on 146 sites. 4 sites dropped due to non-availability of land; 41 MPCS at finishing stage.
Got clearance for the grant of Rs 5 Lakh per MPCS.
Formulated Procedure for formation of Multi-Purpose Cyclone Shelter Management & Maintenance Committee along with Bye Laws.
Underground Cabling (60 Kms)-Tenders for UGC of Digha city under evaluation.
6/6

## Slide 18: AGENDA ITEM (V) : COMPONENT C
Technical Assistance
I. Multi Hazard Risk Assessment (MHRA) Study
Web-based Composite Risk Atlas (CRA) was developed earlier on deterministic model.Phase-II MHRA will be probabilistic modelling.
RFP invited- Tenders under technical evaluation.
II. National Seismic Risk Mitigation Project (NSRMP)
ToR reviewed by World Bank-EoI invited.
III. Hydro-meteorological Resilience Action Plan (HMRAP)
ToR prepared and referred to World Bank for concurrence.
Benefit, Monitoring & Evaluation (BME) study
EoI invited- received EoIs under evaluation.
1/4

## Slide 19: AGENDA ITEM (V) : COMPONENT-C
V. Training and Capacity Building:
i) Shelter Level Training for Community
Cyclone Shelter Management & Maintenance Committee.
Training on Shelter Management, Record Keeping, First Aid, Search & Rescue and refresher training.
Corpus Fund, Task Forces for each MPCS.
Capacity Building of Govt. Officials
5 Training for Trainers (TOT) modules developed and Operational Plan chalked out in Phase I in five priority sectors (Health, Education, Rural Development, Panchayati Raj Institutions, Urban Local Bodies).
19
2/4

## Slide 20: AGENDA ITEM(V) : COMPONENT-C
Modules designed to train Govt. Officials to prepare sector specific Disaster Management Plans utilising Risk/Vulnerability Assessment at State/District/Local Level.
5 National ToT training conducted during January – March 2017 by NIDM. A total of 76 officials participated in the 5 National TOT programmes from 21 States, out of which 48 were from 8 NCRMP States .
State wise allocation of funds under consideration.
20
3/4

## Slide 21: AGENDA ITEM(V) : COMPONENT-C Proposed State Wise Budget Allocation Rs. in Cr.
21
States | Proposed Outlay for Shelter Level Training | Proposed Outlay for Capacity Building Training | Total Proposed Outlay under Component C | Proposed release in 2017-18
Goa | 0.80 | 1.78 | 2.58 | 0.16
Gujarat | 4.00 | 5.71 | 9.71 | 2.18
Karnataka | 0.40 | 0.88 | 1.28 | 0.12
Kerala | 1.08 | 7.45 | 8.53 | 1.48
Maharashtra | 0.52 | 6.38 | 6.90 | 1.25
West Bengal | 2.45 | 3.66 | 6.11 | 1.6
Total | 9.25 | 25.86 | 35.11 | 6.79
4/4

## Slide 22: AGENDA ITEM (VI) : STATUS OF EXTERNAL AUDIT(2016-2017)
External Audit Reports received from PMU/All States except West Bengal . Reports shared with World Bank.
West Bengal to expedite report submission.

## Slide 23: Thank You

## Slide 24
Mitigation Infrastructure | Gujarat | Kerala | Karnataka | Maharashtra | West Bengal | Goa | Total
Cyclone Sheters (Nos) | 112 | 27 | 11 | 13 | 150 | 40 | 353
Roads (kms) | 170 | -- | 110 | -- | -- | 30 | 310
Bridges(Nos.) | -- | -- | 03 | -- | -- | -- | 03
Saline Embankments (Km/No) 11 no. | -- | -- | 10.46 km | 50km | -- | 30 km | 90.46 km
Underground Cabling (Km) | 20km LT 45km HT | -- | -- | 40 km LT 90HT | 20km LT 40HT | 25km LT -- | 105km LT 175HT
NCRMP Phase-II - Physical Outlay (overall)
…

## Slide 25
Component | Gujarat |  | Kerala | Karnataka | Maharashtra | West Bengal |  | Goa | PMU | Total | GoI /World Bank Share | State Share
A-Early warning System | 20.50 |  | 15.00 | 8.90 | 26.60 | 20.50 |  | 19.00 | 0 | 110.50 | 110.50 | 0
B-Cyclone Risk Mitigation Infrastructure |  |  |  |  |  |  |  |  |  |  |  | 
B1 Cyclone Shelters | 305.00 | 136.00 |  | 18.9 | 39.00 | 556.40 | 34.60 |  | 0 | 1089.9 | 817.43 | 272.47
B2 Roads | 165.00 | 0.00 |  | 79.8 | 0.00 | 0.00 | 10.50 |  | 0 | 255.30 | 191.47 | 63.83
B3 Saline Embankments | 0.00 | 0.00 |  | 14.5 | 100.00 | 0.00 | 31.50 |  | 0 | 146.50 | 109.5 | 36.5
B4 Underground Cabling | 100.00 | 0.00 |  | 0.00 | 200.00 | 95.00 | 34.40 |  | 0 | 429.40 | 322.05 | 107.35
C Technical Assistance | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 179.95 | 179.95 | 179.95 | 0
D Implementation Assistance | 28.00 | 7.95 |  | 6.10 | 32.35 | 33.55 | 10.00 |  | 32.35 | 150.30 | 150.30 | 0
Total | 618.50 | 158.9 |  | 128.20 | 397.95 | 705.45 | 140.00 |  | 212.30 | 2361.85 | 1881.20 | 480.15
NCRMP PHASE-II - FINANCIAL OUTLAY (OVERALL)
Rs. In Crore.

## Slide 26
State/Financial Year | Budget Projections |  | Fund released |  | Actual Expenditure | Unspent | Remarks
A. Goa : Outlay Rs 140.00 Crore |  |  |  |  |  |  | No expenditure incurred under Component B till date. On receipt of approval from MHA Rs 0.16 Crore may be released under Component C
2015-16 | 0.00 | 0.00 |  |  | 0.41 |  | 
2016-17 | 40.28 | 24.16 |  |  | 0.33 |  | 
2017-18 | 23.56 | 0.00 |  |  | 0.29 |  | 
Total |  | 24.16 |  |  | 1.03 | 23.13 (96%) | 
B. Gujarat : Outlay Rs 618.50 Crore |  |  |  |  |  |  | 
2015-16 | 170.00 | 96.02 |  |  | 34.47 |  | First instalment of 2017-18 can be released only after full utilisation of unspent balance of Rs 59.07.Crores. Under Component B and Rs 2.36 Cr under Component D. Rs 1.14 Crore may be released under Comp C on receipt of approval from MHA
2016-17 | 194.00 | 79.00 |  |  | 72.42 |  | 
2017-18 | 231.29 | 0.00 |  |  | 6.68 |  | 
Total |  | 175.02 |  |  | 113.57 | 61.43 (35%) | 
C .Karnataka : Outlay Rs 128.20 Crore |  |  |  |  |  |  | 
2015-16 | 32.10 | 1.20 |  | 0.36 |  |  | No expenditure incurred under Component B till date.Rs 0.16 Crore may be released under Comp C on receipt of approval from MHA. Rs 0.60 Cr as First installment of 2017-18 under Component D may be released on receipt of utilization of unspent balance of Rs Rs 0.16 Cr.
2016-17 | 19.75 | 11.25 |  | 0.27 |  |  | 
2017-18 | 8.50 | 0.00 |  | 0.41 |  |  | 
Total |  | 12.45 |  | 1.04 |  | 11.41(92.%) | 
Agenda Item (i): Financial Management – Unspent Balances lying with States as on 31st December 2017
…

## Slide 27
State/Financial Year | Budget Projections (in Crores) |  | Fund released (In Crores) | Actual Expenditure (In Crores) |  | Unspent (In Crores) | Remarks
D. Kerala : Outlay Rs 158.95 Crore |  |  |  |  |  |  | 
2015-16 | 51.24 | 0.44 |  | 0.34 |  |  | No expenditure incurred under Component B till date.Rs 1.49 Crore may be released under Comp C on receipt of approval from MHA Rs 0.60 Cr as First installment of 2017-18 under Component D may be released on receipt of full utilization of unspent balance of Rs 0.14 Cr.
2016-17 | 10.00 | 6.00 |  | 0.33 |  |  | 
2017-18 | 9.00 | 0.00 |  | 0.23 |  |  | 
Total |  | 6.44 |  | 0.90 |  | 5.54 (86%) | 
E. Maharashtra : Outlay Rs 397.95Crore |  |  |  |  |  |  | 
2015-16 | 15.22 | 4.87 |  |  | 0.40 |  | No expenditure incurred under Component B till date.Rs 1.25. Crore may be release under Comp C on receipt of approval from MHA Rs 3.00 Cr as First installment of 2017-18 under Component D may be released on receipt of full utilization of unspent balance of Rs Rs. 2.03 Cr
2016-17 | 57.64 | 29.25 |  |  | 1.44 |  | 
2017-18 | 90.80 | 0.00 |  |  | 1.11 |  | 
Total |  | 34.12 |  |  | 2.95 | 31.17 (91%) | 
F. West Bengal : Outlay Rs 705.45 Crore |  |  |  |  |  |  | 
2015-16 | 75.75 | 45.45 |  |  | 41.17 |  | First instalment of Rs 115.38 Crore (i.e. 60% of the Budget Requirement of 2017-18) released on 02.06.2017. Rs 0.40 Crore may be release under Comp C on receipt of approval from MHA. Rs 75.00 Cr under Component B may be released after the Utilization of Rs 100 Cr. Unspent balance under Component B is Rs 164.71 Cr .as on 31.10.2017. Issue: Large unspent funds available with States-Goa, Maharashtra, Karnataka, Kerala
2016-17 | 224.75 | 224.75 |  |  | 148.13 |  | 
2017-18 | 192.30 | 115.38 |  |  | 28.17 |  | 
Total |  | 385.58 |  |  | 220.87 | 164.71 (43%) | 

## Slide 28: Agenda item (V) : Component-C Proposed Budget Allocation for Capacity Building Training
28
States | No of Trainings proposed | Projection by States (in Crore) | Under Capacity Building Training Program, Uniformity is maintained by keeping: the rate of resource person @Rs.4000/day cost of training per trainee per day @ Rs 2000 3/5 days of training A ceiling of Rs. 15 lakh for misc. expenses
Goa | 70 | 1.78 | 
Gujarat | 330 | 5.71 | 
Karnataka | 30 | 0.88 | 
Kerala | 420 | 7.45 | 
Maharashtra | 180 | 6.38 | 
West Bengal | 168 | 3.66 | 
Total | 1198 | 25.86 | 

## Slide 29: Agenda item (V) : Component-C Proposed Budget Allocation for Shelter Training
29
States | No of Trainings proposed | Projection by States (in Crore) | Proposed Outlay (in Crore)
Goa | 20 | 1.82 | 0.80
Gujarat | 100 | 5.95 | 4.00
Karnataka | 10 | 0.74 | 0.40
Kerala | 27 | 1.44 | 1.08
Maharashtra | 13 | 0.92 | 0.52
West Bengal | 150 | 2.45 | 2.45
Total | 320 | 13.32 | 9.25

## Slide 30
Agenda Item (Vi) Status of External Audit
Sl. No. | Name of State | Period up to which completed | Observations, if any | Action Taken
1 | Gujarat * | 31.03.2017 | Shared with World Bank | Accepted by World Bank upto 31.03.2016
2 | Karnataka | 31.03.2017 | Shared with World Bank. Total ineligible expenditure of Rs 7.69 lakh. | Clarifications sought from SPIU
3 | Kerala | 31.03.2016 | Audit Report for 2016-17 received | Reminder sent to the State for early submission
4 | Goa | 31.03.2016 | Audit Report for 2016-17 recieved | Reminder sent to the State for early submission
5 | West Bengal | 31.03.2016 | Amount of Rs 5.02 Crore has been disallowed for 2015-16. Audit Report for 2016-17 not recieved. | Clarifications sought from SPIU and reminder for Audit Re[ort 2016-17 already sent
6 | Maharashtra | 31.03.2017 | Shared with World Bank. | 
* Audit done by Chartered Accountant firm

## Slide 31: BE/RE-2017-18 Actual Expenditure upto Dec,2017, Anticipated Expenditure for last Quarter
Demand No. & Name | 46- MINISTRY OF HOME AFFAIRS |  |  |  |  |  |  |  |  | (In thousands)
Major Head/Minor Head/Sub head/object head | BE 2017-2018 | RE 2017-2018 | Actual Exp upto Dec 17 | Anticipated Exp Upto Dec 2017 | Anticipated Exp for 4th Qtr. | Jan,18 | Feb,18 | Mar, 18 | TOTAL | Remarks
2245 | 2017-18 |  |  |  |  |  |  |  |  | 
01-Salaries | 8000 | 10000 | 8078 |  | 1922 | 961 | 961 |  | 10000 | 
06-Medical Treatment | 300 | 200 | 14 |  | 186 | 50 | 50 | 86 | 200 | 
11-Domestic Travel Expenses | 700 | 700 | 537 |  | 163 | 60 | 70 | 33 | 700 | 
12-Foreign Travel Exp. | 500 | 100 | 0 |  | 100 |  |  | 100 | 100 | 
13-Office Expenses | 2500 | 2500 | 1783 |  | 717 | 250 | 250 | 217 | 2500 | 
20-Other Admn Exp | 200 | 200 | 50 |  | 150 | 60 | 20 | 70 | 200 | 

## Slide 32: Contd..
20-Other Admn Exp | 200 | 200 | 50 |  | 150 | 60 | 20 | 70 | 200 | 
26-Adv & Pub | 200 | 200 | 129 |  | 71 | 71 |  |  | 200 | 
28-Prof. Service | 30000 | 20000 | 7696 |  | 12304 | 400 | 7900 | 4004 | 20000 | Rs 12 lakh fees of specialists, Rs 25 Lakh for BME, Rs 80 Lakh release to NIDM, balance Rs 9.08 lakh to TCIL
50-other charges | 100 | 0 | 0 |  | 0 |  |  |  | 0 | 
Total of 2245 | 42500 | 33900 | 18287 | 0 | 15613 | 1852 | 9251 | 4510 | 33900 | 
3601 |  |  |  |  | 0 |  |  |  | 0 | 
31- Grant in aid General | 700000 | 270000 | 103400 | 103400 | 166600 |  | 50000 | 116600 | 270000 | Anticipated release to be made under component C and D to Phase I & Phase II states amounting to Rs. 16.66 Crore as per Annex B
35- Creation of capital asset | 6200000 | 6000000 | 4561700 | 4561700 | 1438300 | 340000 | 350000 | 748300 | 6000000 | Anticipated release to be made under component A -Rs. 34 Crore to Odisha in Jan, Rs.32.63 Crores for Andhra Pradesh Under Component A (U/S Rs 6.59 cr -full utilisation) and expected release of Rs. 44.17 Crore (U/S Rs 59 cr- full utilisation) to Gujarat and Rs 33.12 Crore (U/S Rs 66 cr - on utilization of Rs 41 Crore with balance U/S of Rs 25 crore) to Odisha under comp B.
Total of 3601 | 6900000 | 6270000 | 4665100 | 4665100 | 1604900 |  |  |  | 6270000 | 
Grand Total | 6942500 | 6303900 | 4683387 | 4665100 | 1604900 |  |  |  | 6303900 | 

## Slide 33
Demand No. & Name | 46- MINISTRY OF HOME AFFAIRS |  |  |  |  |  |  |  |  | (In thousands)
Major Head/Minor Head/Sub head/object head | BE 2017-2018 | RE 2017-2018 | Actual Exp upto Dec 17 | Anticipated Exp Upto Dec 2017 | Anticipated Exp for 4th Qtr. | Jan,18 | Feb,18 | Mar, 18 | TOTAL | Remarks
3601 |  |  |  |  | 0 |  |  |  | 0 | 
31- Grant in aid General | 700000 | 270000 | 103400 | 103400 | 166600 |  | 50000 | 116600 | 270000 | Anticipated release to be made under component C and D to Phase I & Phase II states amounting to Rs. 16.66 Crore as per Annex B
35- Creation of capital asset | 6200000 | 6000000 | 4561700 | 4561700 | 1438300 | 340000 | 350000 | 748300 | 6000000 | Anticipated release to be made under component A -Rs. 34 Crore to Odisha in Jan, Rs.32.63 Crores for Andhra Pradesh Under Component A (U/S Rs 6.59 cr -full utilisation) and expected release of Rs. 44.17 Crore (U/S Rs 59 cr- full utilisation) to Gujarat and Rs 33.12 Crore (U/S Rs 66 cr - on utilization of Rs 41 Crore with balance U/S of Rs 25 crore) to Odisha under comp B. (Total- 143 cr)
Total of 3601 | 6900000 | 6270000 | 4665100 | 4665100 | 1604900 |  |  |  | 6270000 | 
BE/RE-2017-18 Actual Expenditure upto Dec,2017, Anticipated Expenditure for last Quarter in respect of 3601- Grant-in Aid Transfer to State

## Slide 34: Annex B
Details of Release anticipated under Comp C & D - Rs 11.66 crores |  |  |  | 
 | Comp | Amount | States | Remarks
Phase-I | C | 0 | Andhra Pradesh/ Odisha | 
Phase-I | D | 1.78 | Andhra Pradesh | Already eligible for release- Unspent 20.00 lakh
Phase-I | D | 3.20 | Odisha | Already eligible for release- Unspent 2.02 crore
Phase-II | C | 6.79 |  | Annexure A
Phase-II | D | 0.60 | Kerala | Unspent Balance 3.0 lakh
Phase-II | D | 1.92 | West Bengal | Already eligible for releas-Unspent Balance 1.11 crore
Phase-II | D | 1.37 | Gujarat | Subject to full utilisation of unspent 2.23 crore
Phase-II | D | 1.00 | Maharashtra | Subject to full utilisation of unspent 1.77 crore
 |  | 16.66 |  |